## Disclaimer
11th Hour Racing team
Sustainable design and build report - 2021
Supporting the main report, this document - Lifecycle Inventory identifies the various components of the design and build process that were included in the lifecycle analysis
Date & version: 14th October 2021
sustainability@1degree.us
DISCLAIMER The team’s LCA results were calculated using MarineShift360. Backed by 11th Hour Racing as Founding Sponsor, MarineShift360 is a purpose-built marine industry life cycle assessment tool. MarineShift360 is an ISO 14040:2006 & ISO 14044:2006 compliant and certified life cycle assessment tool. LCA results herein are calculated using MarineShift360, which is under development and is currently in beta stage. No statements regarding accuracy are made and results may change over time as the development of MarineShift360 continues.

## 11-2 Overview
|  |  |  | Project tracking | [16 empty] | TOR Workshop |  |  | Publish SD&B Report |  |  | TJV village open
|  |  |  | Item |  |  |  |  | Notes | w/c 19 July |  | w/c 26 July | w/c 2 Aug | w/c 9 Aug |  | w/c 16 Aug | w/c 23 Aug | w/c 30 Aug |  | w/c 6 Sep | w/c 13 Sep | w/c 20 Sep | w/c 27 Sep | w/c 4 Oct | w/c 11 Oct | w/c 18 Oct | w/c 25 Oct | w/c 1 Nov | w/c 8 Nov
A |  |  |  | Check inventory for completeness with BE
All |  |  |  | Chase remaining suppliers for data
[7 empty] | D | Guelt | DF met, Catch up with Ben to work out best way forwards
[7 empty] | D | Hydroem | Ram, hoses and plc box. Contact - Michel (ops manager), Natalie and one other young technician. AM to follow up machined pieces (RAM) and hyrdaulics. AM emailed forms to Nathalie and Michel 19/7
[7 empty] | D | Nanni
[7 empty] | A | Persico | AM chased 19/7, ernesto replied and confirmed data will come in next 2 weeks, data received
[7 empty] | A | Multiplast | AM emailled Romain with input spreadsheet
[7 empty] | A | Harken | All received
[7 empty] | A | C3 | Rudders and fin section of keel (?), and possibly 2 foils. DF visited on 19/7. AM followed up 19/7 with Pierre Alexis Michel. Pierre trying to finish by COP 31st aug, call in calendar to help
[7 empty] | A | Southern Spars | AM sent chasing email to Nuria 19/7 - data received
[7 empty] | D | GVD | Design hours captured
[7 empty] | E | CDK Design phase | 3-4 people
[7 empty] | E | PSM | DF follow up
[7 empty] | E | CDK | Port foil (can do twice the starboard foil)
[7 empty] | E | Nautiscan | NDT - no template - design inclusion?
[7 empty] | A | North Sails | AM reply to Manuel 21/7 - include marlow info
[7 empty] | E | Blackfibre | Damian will call guillaume 21/7
[7 empty] | A | JP3 | Rudder bearings, and larger alu component. Contact: Pierre Antoine. AM set metal/machined part form in french 19/7
[7 empty] | A | Marlow | AM chased paul honess, and chased napper and chris noble for rigging spec. Sorted with Chris
[7 empty] | A | Carbon instinct | AM sent spreadsheet to Sam
[7 empty] | A | AMPM | AM spoke to Imogen 19/7 - said will have all infor by end of Jluy
[7 empty] | A | KZ
[7 empty] | A | Karver
[7 empty] | A | Prot-Design3D | Damian visited on 16/7, AM followed up by email with forms on 16/7
[7 empty] | A | Future Fibres | Talk to nuria - standing rigging
[7 empty] | A | Navico | AM chased - greta
[7 empty] | A | Lorima | AM spoke to Imogen 19/7 - said will have all infor by end of Jluy
[7 empty] | A | Diverse | Sifi keen to catch up w/c 26/Aug
[7 empty] | A | Cariboni | Spreadsheet coming next week (6th)
[7 empty] | A | Pesch
[7 empty] | A | Celtinox | (stanchions)
|  |  |  | NEW TIMELINE - both configurations | [13 empty] | Transfer - Monday 30th
Add other suppliers by Weds 1st
Weds 1st - Reach out to Michel for gaps for the remaining components
Process remaining data
Write additions to Etienne report
Share ISO report
Recomendations and case studies
E,A |  |  |  | Process data (input into tool)
E |  |  |  | CASE STUDIES: 1. Foil case study; Mould / out of plan / hybrid? 2. Energy/commuter travel/component transport study 3. Late rule change impacts 6-4 degrees 4. 100% biocomposites 'imagining net zero' scenario |  |  |  |  | https://www.youtube.com/watch?v=sJih1bdlaOw&t=313s
E,A |  |  |  | Draft ISO report text for functional unit scenario 1 - Launch configuration
E,A |  |  |  | Draft ISO report text for functional unit scenario 2 - Race configuration
D |  |  |  | Prepare slides for workshop
E,A |  |  |  | Finalise ISO Report for functional unit scenario 1 - Launch configuration
E,A |  |  |  | Finalise ISO Report for functional unit scenario 2 - Race configuration
E,A |  |  |  | Transfer - craig
E,A |  |  |  | Extrapolation - michel
All |  |  |  | Draft SD&B Report LCA chapter
All |  |  |  | MS360 2nd party review
All |  |  |  | Finalise SD&B Report LCA chapter
Sign off with 11hr
Design and translation of report
All |  |  |  | Publish
LCA system
|  |  | Hull & Deck | [6 empty] | Appendages |  |  | Sails |  |  |  | Rigging |  |  | Deck Hardware | Design | Electronics | Hydraulics | Propulsion
| Plugs and moulds | Hull | Deck | Structure |  | Misc. composite parts |  | Rudders |  | Keel |  | Foils | Sails | Boom |  | Mast | Outriggers | Running Rigging | Standing rigging | Deck Hardware | Design | Electronics | Hydraulics | Propulsion | [5 empty] | Data quality hierarchy
| Hull Plug | Hull shell | Deck shell | Hull and deck assembly | - | Jockey pole |  | Rudder case |  | Keel fin |  | Foils | Main sail | Boom |  | Mast | Outriggers | Core | Standing rigging | Deck Gear | Design | Displays | Deck hydraulic system | Engine, drive shaft and propeller | [5 empty] | 1. Extracted from inventory software or input forms, exact numbers
2. Extrapolated from similar componet input forms
| Hull mould |  |  | Bulkheads |  | Chain plates |  | Rudder moulds; blades and stock |  | Keel trailing edge | - |  | J2 | Boom hardware | - | Mast hardware | Outrigger hardware | Covers |  | Furlers |  | Sensors | Keel hydraulic system | [6 empty] | 3. Based on observations but not input data
4. Supported by Michel theoretical study
| Deck plug |  |  | Tunnel |  | Winch pods |  |  |  | Keel bulb |  |  | J3 |  |  |  |  | Dockline |  | Life Lines and Pulpit |  | Computing | [7 empty] | 5. Estimate
| Deck mould |  |  | Longitudinal girders |  | Hatches |  |  |  | Keel bearings |  |  | J15 | [6 empty] | Steering System |  | Batteries
| Deck mock up |  |  | Cockpit |  | Coach roof | [6 empty] | MH0 | [6 empty] | Winches and Transmission |  | Cables
|  |  |  | Ballast |  | Bowsprit; plug, mould, part | [6 empty] | FR0 | [8 empty] | Electric Motors
|  |  |  | Consumables and utilities |  | Composite ballast pipes | [6 empty] | J0 | [8 empty] | Other
|  |  |  | Keel box; plug, mould and part |  | Painting | [6 empty] | A7 | [10 empty] | KEY
|  |  |  | Keel Tower | [8 empty] | A2 | [10 empty] | GROUP
|  |  |  | Foil cases | [8 empty] | Storm jib | [10 empty] | SUBGROUP
|  |  |  | Foil case structure | [19 empty] | ASSESSMENT
|  |  |  | Functional unit: |  |  |  | 11th Hour Racing Team optimised for TOR campaign
|  |  | Construction | [6 empty] | Appendages | [5 empty] | Rigging |  |  |  | Deck Hardware | Design | Electronics | Hydraulics | Engine
|  | Hull | Deck | Structure |  | Other parts |  | Rudders |  | Keel |  | Foils | Sails | Boom |  | Mast | Outriggers | Running Rigging | Standing rigging
[8 empty] | Rudders x1; blades and stocks |  |  |  | Foils x1 (TBC/C3?) | Main sail x 2 |  |  |  |  | Core x 1 | Stays x 1
[13 empty] | J2 x 1 |  |  |  |  | Covers x 1 | Shrouds x 1
[13 empty] | J3 x 1 |  |  |  |  | Dockline x 1 | Runners x 1
[13 empty] | J15 x 1 |  |  |  |  | Fenderline x 1 | Hardware x 1
MH0 x 1
FR0 x 1
J0 x 1
A7 x 1
A2 x 1
|  |  |  | Functional unit: |  |  |  | 11th Hour Racing Team optimised for TOR campaign
|  |  |  | Construction | [5 empty] | Appendage | [5 empty] | Rigging |  |  |  | Fit out
|  |  |  | Assemblies |  |  |  | Rudder |  | Keel |  | Foils | Sails | Boom |  | Outriggers
|  |  |  | Bulkheads | [5 empty] | Keel fin |  | Foils 1 - CDK | Main sail x 3 | Boom |  | Outrigger x 2
|  |  |  | Deck | [5 empty] | Keel trailing edge |  | Foils 2 - C3 (not ordered - TBC) | J2 x 2 | Boom hardware
|  |  |  | Hull | [5 empty] | Keel bulb |  |  | J3 x 2 | Boom air freight
|  |  |  | Structure | [8 empty] | J15 x 2
|  |  |  | Other parts | [8 empty] | MH0 x 2
FR0 x 2
J0 x 2
A7 x 2
A2 x 2
Storm jib x 1
[12 empty] | Etienne extended til end of TJV - would be able to achieve..... | [6 empty] | Dates
[12 empty] | Current Status | CDK LCA will be complete by Monday dat ainput and calc (not interpretation) | [5 empty] | Now - 20/9/21
[12 empty] | Next step | Support to complete additional appendages and components | [5 empty] | 20/9/21 - 27/9/21
[12 empty] | Extra time | Interpretation of results (plus waste and energy case studies) | [5 empty] | 27/9/21 - 5/10/21
[13 empty] | Run sensitivity studies and case studies | [5 empty] | 5/10/21 - 19/10/21
[13 empty] | Make full set of conclusions and recommendations | [5 empty] | 12/10/21 -19/10/21 (In parallel)
[13 empty] | Internal review and translation | [5 empty] | 19/10/21 - 27/10/21
[13 empty] | Produce and share with stakeholder reports (report/poster) | [5 empty] | 19/10/21 - 27/10/21
[13 empty] | Outreach and presentations at TJV | [5 empty] | 27/10/21 - 7/11/21